## Bond Budget (Rev)
Measure JJ Bond Program Reconciled Budget Summary Report
As of 12/31/2017
INCOME |  |  | SERIES 1 REVENUES | EXPENDED TO-DATE | % EXPENDED
Bond Series 1A | 2009-05-07 |  | 54004963
Bond Series B (BABS) | 2009-05-07 |  | 12000000
Bond Series 1C | 2009-06-23 |  | 70017065
Bond Interest (Received) |  |  | 4130672.63
Subtotal |  |  | 140152700.63 | 132655480.4 | 94.65%
BUDGET/EXPENSE |  | ORIGINAL BUDGET | REVISED BUDGET | EXPENDED TO-DATE | % EXPENDED
2017-12-31
Available Program Contingency |  | 3975875.24 | -0.1 | 0 | 0%
1997 Certificate of Participation |  | 52206346 | 52206346 | 52206346 | 100%
Other Bond Related Costs |  | 3230867 | 3230867 | 3230867 | 100%
Victor Valley College Regional Public Safety Training Center
Total RPSTC |  | 31930956 | 31930955.99 | 31930955.8 | 100%
Victor Valley College Workforce Development Center - Phase 1
Total Workforce Development Center |  | 11324985 | 11016624 | 11016624 | 100%
Main Campus
Hesperia Site |  | 36917 | 37651.76 | 37651.76 | 100%
Music Building Code Compliance & Renovation |  | 3800000 | 3535675 | 3535675.22 | 100%
- Architectural
- Fiber Survey and relocation
- Abatement
- Construction
- DSA Plan Check Fees
- Soils Engineering
Health Science Building Expansion |  | 14400000 | 11327136 | 11327135.77 | 100%
Main Campus Solar CPV (Bond only) |  | 2557322 | 3001963 | 3001963 | 100%
Vocational Complex Expansion/Renovation |  | 6500000 | 6600000 | 6298902.83 | 95.44%
- Agriculture |  |  | 100000
One Stop |  | 19829 | 7853736.11 | 757612.51 | 9.647%
Main Campus Other
| BUDGET | 10077774 | 9311746 | 9311746.51
Solar Covered Parking |  | 2007916 | 2007915 | 2007915.46 | 100%
Energy Projects |  | 1868547 | 1765912 | 1765912 | 100%
Campus Roadway & Parking Lot Improvements |  | 2833125 | 2470092 | 2470092 | 100%
Gymnasium HVAC Upgrades |  | 630570 | 544945 | 544945 | 100%
Campus I.T. Upgrades |  | 488405 | 488405 | 488405 | 100%
Program Consultants |  | 312755 | 312755 | 312755 | 100%
Program Manager |  | 1132817 | 1132817 | 1132817 | 100%
Legal Fees |  | 98997 | 98997 | 98997 | 100%
Architectual/Engineering/Testing |  | 348304 | 348304 | 348304 | 100%
Other |  | 356338 | 141604 | 141604.05 | 100%
BOND JJ FUND TOTALS |  | 140060871.24 | 140152700.76 | 132655480.4 | 94.65%
Note on E14: $7,633,177 to One-Stop project
Note on E32: Add'l $100k needed for equip installations
Note on E34: $7,613,177 bal from Conting.

## Bond Budget
Measure JJ Bond Program Reconciled Budget Summary Report
As of 09/30/2017 (Includes Updated Budgets)
| INCOME |  |  |  | SERIES 1 REVENUES | EXPENDED TO-DATE | % EXPENDED
1 | Offering 1 | Bond Series 1A | 2009-05-07 |  | 54004963
2 |  | Bond Series B (BABS) | 2009-05-07 |  | 12000000
3 |  | Bond Series 1C | 2009-06-23 |  | 70017065
4 |  | Bond Interest (Received) |  |  | 4110438.51
5 |  | Subtotal |  |  | 140132466.51 | 131954037.47 | 94.16%
| BUDGET/EXPENSE |  |  | ORIGINAL BUDGET | REVISED BUDGET | EXPENDED TO-DATE | % EXPENDED
2017-09-30
6 |  | Available Program Contingency |  | 3975875.24 | 7833176.9 | 0 | 0%
7 |  | 1997 Certificate of Participation |  | 52206346 | 52206346 | 52206346 | 100%
9 |  | Other Bond Related Costs |  | 3230867 | 3230867 | 3230867 | 100%
10 |  | Victor Valley College Regional Public Safety Training Center
11 |  | Total RPSTC |  | 31930956 | 31930955.99 | 31930955.8 | 100%
12 |  | Victor Valley College Workforce Development Center - Phase 1
13 |  | Total Workforce Development Center |  | 11324985 | 11016624 | 11016624 | 100%
14 |  | Main Campus
15 |  | Music Building Code Compliance & Renovation |  | 3800000 | 3535675 | 3535675.22 | 100%
16 |  | - Architectural
17 |  | - Fiber Survey and relocation
18 |  | - Abatement
19 |  | - Construction
20 |  | - DSA Plan Check Fees
21 |  | - Soils Engineering
22 |  | Health Science Building Expansion |  | 14400000 | 11327136 | 11327135.77 | 100%
23 |  | Design/Build Team
24 |  | - Soils /Engineering
25 |  | - DSA Plan Check Fees
26 |  | Vocational Complex Expansion/Renovation |  | 6500000 | 6500000 | 6154747.03 | 94.69%
27 |  | - Architectural
28 |  | - Soils/ Engineering
29 |  | - Construction
30 |  | Main Campus Solar CPV (Bond only) |  | 2557322 | 3001963 | 3001963 | 100%
|  | One Stop |  | 19829 | 200324.99 | 200325.38 | 100%
- Architectural
31 |  | Hesperia Site |  | 36917 | 37651.76 | 37651.76 | 100%
32 |  | Main Campus Other |  | 10077774 | 9311746 | 9311746.51
33 |  | Solar Covered Parking |  | 2007916 | 2007915 | 2007915.46 | 100%
34 |  | Campus Wide Key Card Access |  | 0 | 0 | 0 | 0%
35 |  | Energy Projects |  | 1868547 | 1765912 | 1765912 | 100%
36 |  | Campus Roadway & Parking Lot Improvements |  | 2833125 | 2470092 | 2470092 | 100%
37 |  | Campus wide Surveillance system |  | 0 | 0 | 0 | 0%
38 |  | Gymnasium HVAC Upgrades |  | 630570 | 544945 | 544945 | 100%
39 |  | Campus I.T. Upgrades |  | 488405 | 488405 | 488405 | 100%
40 |  | Program Consultants |  | 312755 | 312755 | 312755 | 100%
41 |  | Program Manager |  | 1132817 | 1132817 | 1132817 | 100%
42 |  | Legal Fees |  | 98997 | 98997 | 98997 | 100%
43 |  | Architectual/Engineering/Testing |  | 348304 | 348304 | 348304 | 100%
44 |  | Other |  | 356338 | 141604 | 141604.05 | 100%
45 |  | BOND JJ FUND TOTALS |  | 140060871.24 | 140132466.64 | 131954037.47 | 94.16%

## 0006 expenditures
|  | 2008/09 | 2009/10 | 2010/11 | 2011/12 | 2012/13 | TOTAL
1 | Daily Press |  | 1551 | 1945 | 440 |  | 3936 | 133518
1 | High Tech Signs |  | 577 |  |  |  | 577
1 | Revolving Cash |  | 50 | 11731 | 13608 |  | 25389
1 | Bell Mountain |  |  | 5969 |  |  | 5969
1 | City of Victorville |  |  | 26964 |  |  | 26964
1 | Compview |  |  | 9555 |  |  | 9555
1 | Pacific Parking Systems |  |  | 62706 |  |  | 62706
1 | PO 95609/Dup Pmt |  |  | -258 |  |  | -258
1 | 8/30 M&O Invoice |  |  |  | 514 |  | 514 |  | 1 Other
1 | CED Supplies |  |  |  | 3677 |  | 3677
1 | To Pgrm 0040 |  |  |  | -940 |  | -940 |  | 2 Consultants
1 | Apex Rentals |  |  |  | 730 |  | 730
1 | Reimb DSA TST/INSP |  |  |  | -14055 |  | -14055 |  | 3 Architectual / Inspection
1 | Corr PO 100215 |  |  |  |  | 1254 | 1254
1 | SCE |  |  |  |  | 7500 | 7500 |  | 4 I.T. Upgrades
2 | Dudek |  | 63356 | 4876 |  |  | 68232 | 312755
2 | James Lents |  | 12727 |  |  |  | 12727 |  | 5 Roadway improvements
2 | Cleartech Media |  |  | 42222 |  |  | 42222
2 | Merrell Eng |  |  | 1840 | 25788 | 41018 | 68646 |  | 6 Compass Energy Projects
2 | P2S Engineering |  |  | 49150 |  |  | 49150
2 | Total Environment |  |  | 13350 |  |  | 13350 |  | 7 Gym HVAC
2 | Gale/Jordan |  |  |  | 7010 |  | 7010
2 | Namdar Structural |  |  |  | 17820 |  | 17820 |  | 8 Legal
2 | James Spencer |  |  |  | 35196 |  | 35196
2 | To Prgm 0015 |  |  |  |  | -1598 | -1598 |  | 9 Program manager
3 | Frick, Frick & Jette |  | 11226 | 190596 | 82775 |  | 284597 | 338904
3 | A&E Inspection |  |  | 6480 |  | 1400 | 7880
3 | Carrier Johnson |  |  | 46427 |  |  | 46427
4 | Impex |  |  | 309297 |  |  | 309297 | 488405
4 | Vector |  |  | 170529 | 8579 |  | 179108
5 | Cooley Construction |  | 330644 | 207738 | 2262354 |  | 2800736 | 2470092
5 | Pkg Lot Repairs to F01 |  | -529482 |  |  |  | -529482
5 | Liq Pgk Lot Repairs/Do Intrfnd |  |  | 529482 |  |  | 529482
5 | PY Pkg Lot Repairs |  |  | -330644 |  |  | -330644
6 | Compass |  |  | 228430 | 1671471 | 440403 | 2340304 | 2340304
7 | Air-Ex Air Conditioning |  |  | 544945 |  |  | 544945 | 544945
8 | Stutz Artiano Shinoff & Holtz |  | 69945 | 13654 | 5084 | 10139 | 98822 | 98822
9 | GGK/CCS Group | 195043 | 543110 | 380276 | 8448 | 5940 | 1132817 | 1132817
|  | 195043 | 503704 | 2528516 | 4128499 | 506056 | 7860562 | 7860562